## English_DeepICR_1st_sprint
En_DeepICR WBS
PROJECT START DATE |  |  |  | 2020-06-29 |  | End Date |  |  | 2020-09-03 | [8 empty] | July | [22 empty] | August | [20 empty] | September
Sprint | Task | Resource allocaiton | Machine allocation | Priority | Start | Finish | Duration | Duration in hours | Status | % Complete | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15
[11 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
Project Summary | Subtask | Resource | NSL machine |  | 2020-06-23 | 2020-09-22 | 66 day(s) | Hours |  | 1.385% | 22 | 23 | 24 | 25 | 26 | 29 | 30 | 1 | 2 | 3 | 6 | 7 | 8 | 9 | 10 | 13 | 14 | 15 | 16 | 17 | 20 | 21 | 22 | 23 | 24 | 27 | 28 | 29 | 30 | 31 | 3 | 4 | 5 | 6 | 7 | 10 | 11 | 12 | 13 | 14 | 17 | 18 | 19 | 20 | 21 | 24 | 25 | 26 | 27 | 28 | 31 | 1 | 2 | 3 | 4 | 7 | 8 | 9 | 10 | 11 | 14 | 15 | 16 | 17 | 18 | 21 | 22 | 23 | 24 | 25 | 28 | 29
Task | Subtask | Resource |  |  | 2020-06-23 | 2020-07-30 | 28 day(s) | 224 hour(s) | bar: WEEK 5 M 13; WEEK 7 M 27 to WEEK 8 T 4; WEEK 9 R 13
Data Preprocessing | Analysis data Preprocessing Requirement | saiful |  | Medium | 2020-06-23 | 2020-06-23 | 1 day(s) | 8 hour(s) | Open | 50% | bar: WEEK 2 W 24; WEEK 5 M 13; WEEK 7 T 28 to WEEK 8 T 4; WEEK 9 R 13
| Data Acquisition | saiful |  | Medium | 2020-06-24 | 2020-06-24 | 1 day(s) | 8 hour(s) | Running | 30% | bar: WEEK 2 R 25; WEEK 5 M 13; WEEK 7 T 28 to WEEK 8 T 4; WEEK 9 R 13
| Data review | saiful |  | Medium | 2020-06-25 | 2020-06-25 | 1 day(s) | 8 hour(s) | Completed | 0% | bar: WEEK 2 F 26; WEEK 5 M 13; WEEK 7 T 28 to WEEK 8 T 4; WEEK 9 R 13
| Categorizing Benchmark data | saiful |  | Medium | 2020-06-25 | 2020-06-25 | 1 day(s) | 8 hour(s) | Open | 0% | bar: WEEK 3 M 29; WEEK 5 M 13; WEEK 7 T 28 to WEEK 8 T 4; WEEK 9 R 13
| Semi-annotation DDI-100 and Receipt dataset for layout annotaion | saiful |  | Medium | 2020-07-25 | 2020-07-30 | 4 day(s) | 32 hour(s) | Running | 0% | bar: WEEK 3 M 29 to WEEK 3 T 30; WEEK 5 M 13; WEEK 7 T 28 to WEEK 8 T 4; WEEK 9 R 13
| Data cropping and making html chunk |  |  |  | 2020-07-15 | 2020-07-15 | 1 day(s) | 8 hour(s) | Running | 0% | bar: WEEK 5 M 13; WEEK 5 W 15; WEEK 7 T 28 to WEEK 8 T 4; WEEK 9 R 13
AWS instance creation and using | bar: WEEK 5 M 13; WEEK 7 T 28 to WEEK 8 T 4; WEEK 9 R 13
| Documentation | saiful |  | Medium | 2020-07-01 | 2020-07-01 | 1 day(s) | 8 hour(s) | Open | 0% | bar: WEEK 3 T 30; WEEK 5 M 13; WEEK 7 T 28 to WEEK 8 T 4; WEEK 9 R 13
Task | Subtask | Resource |  |  | 2020-07-01 | 2020-08-24 | 39 day(s) | 312 hour(s) | bar: WEEK 5 M 13; WEEK 7 T 28 to WEEK 8 T 4; WEEK 9 R 13
Layout Analysis | Data semi annotation | saiful |  | Medium | 2020-07-01 | 2020-07-02 | 2 day(s) | 16 hour(s) | Open | 0% | bar: WEEK 3 W 1 to WEEK 3 R 2; WEEK 5 M 13; WEEK 7 T 28 to WEEK 8 T 4; WEEK 9 R 13
| Annotation of data | saiful |  | Medium | 2020-07-03 | 2020-07-14 | 8 day(s) | 64 hour(s) | Open | 0% | bar: WEEK 3 F 3 to WEEK 5 T 14; WEEK 7 R 30 to WEEK 8 T 4; WEEK 9 R 13
| Review Annotated Data | NSL team |  | Medium | 2020-07-04 | 2020-07-16 | 9 day(s) | 72 hour(s) | Open | 0% | bar: WEEK 4 M 6 to WEEK 5 R 16; WEEK 7 R 30 to WEEK 8 T 4; WEEK 9 R 13
| Data preparation |  |  | Medium | 2020-07-16 | 2020-07-17 | 2 day(s) | 16 hour(s) | Open | bar: WEEK 5 M 13 to WEEK 5 T 14; WEEK 5 R 16 to WEEK 5 F 17; WEEK 7 R 30 to WEEK 8 T 4; WEEK 9 R 13
| Model Building : Iteration 1 Training | saiful |  | Medium | 2020-07-17 | 2020-07-27 | 7 day(s) | 56 hour(s) | Open | 0% | bar: WEEK 5 M 13 to WEEK 5 T 14; WEEK 5 F 17 to WEEK 7 M 27; WEEK 7 R 30 to WEEK 8 T 4; WEEK 9 R 13
| Model Building : Iteration 1 Testing | saiful Kazal |  | Medium | 2020-07-28 | 2020-07-28 | 1 day(s) | 8 hour(s) | Open | 0% | bar: WEEK 5 M 13 to WEEK 5 T 14; WEEK 7 T 28; WEEK 7 R 30 to WEEK 8 T 4; WEEK 9 R 13
| Model Building : Iteration 2 Training | saiful |  | Medium | 2020-07-30 | 2020-08-07 | 7 day(s) | 56 hour(s) | Open | 0% | bar: WEEK 5 M 13 to WEEK 5 T 14; WEEK 6 M 20 to WEEK 6 R 23; WEEK 7 R 30 to WEEK 9 M 10; WEEK 9 R 13
| Model Building : Iteration 2 Testing | saiful Kazal |  | Medium | 2020-08-10 | 2020-08-10 | 1 day(s) | 8 hour(s) | Open | 0% | bar: WEEK 5 M 13 to WEEK 5 T 14; WEEK 6 M 20 to WEEK 6 R 23; WEEK 7 R 30 to WEEK 9 M 10; WEEK 9 R 13
| Model Building : Iteration 3 Training | saiful |  | Medium | 2020-07-30 | 2020-08-07 | 7 day(s) | 56 hour(s) | Open | 0% | bar: WEEK 5 M 13 to WEEK 5 T 14; WEEK 7 R 30 to WEEK 8 F 7; WEEK 9 R 13
| Model Building : Iteration 3 Testing | saiful |  | Medium | 2020-08-10 | 2020-08-10 | 1 day(s) | 8 hour(s) | Open | 0% | bar: WEEK 5 M 13 to WEEK 5 T 14; WEEK 7 R 30 to WEEK 8 T 4; WEEK 9 M 10; WEEK 9 R 13
| Model Building : Iteration 4 Training including JP data | saiful |  | Medium | 2020-07-30 | 2020-08-07 | 7 day(s) | 56 hour(s) | Open | bar: WEEK 5 M 13 to WEEK 5 T 14; WEEK 7 R 30 to WEEK 8 F 7; WEEK 9 R 13
| Model Building : Iteration 4 Testing including JP data | saiful |  | Medium | 2020-08-10 | 2020-08-10 | 1 day(s) | 8 hour(s) | Open | bar: WEEK 5 M 13 to WEEK 5 T 14; WEEK 7 R 30 to WEEK 8 T 4; WEEK 9 M 10; WEEK 9 R 13
| Unit testing And performance measure | kazal Saiful |  | Medium | 2020-08-10 | 2020-08-24 | 11 day(s) | 88 hour(s) | Open | 0% | bar: WEEK 5 M 13 to WEEK 5 T 14; WEEK 7 R 30 to WEEK 8 T 4; WEEK 9 M 10 to WEEK 11 M 24
| Code Cleaning | saiful |  | Medium | 2020-08-03 | 2020-08-03 | 1 day(s) | 8 hour(s) | Open | 0% | bar: WEEK 5 M 13; WEEK 7 R 30 to WEEK 8 T 4; WEEK 9 R 13
| Documentation | saiful |  | Medium | 2020-08-04 | 2020-08-04 | 1 day(s) | 8 hour(s) | Open | 0% | bar: WEEK 5 M 13; WEEK 7 R 30 to WEEK 8 T 4; WEEK 9 R 13
Task | Subtask | Resource |  |  | 2020-07-08 | 2020-08-21 | 33 day(s) | 264 hour(s) | bar: WEEK 5 M 13; WEEK 7 R 30 to WEEK 8 T 4; WEEK 9 R 13
Table Detection | Data semi automation |  |  | Medium | 2020-07-08 | 2020-07-10 | 3 day(s) | 24 hour(s) | Open | 0% | bar: WEEK 4 W 8 to WEEK 5 M 13; WEEK 7 R 30 to WEEK 8 T 4; WEEK 9 R 13
| Annotation of data | murtoza vai |  | Medium | 2020-07-16 | 2020-07-24 | 7 day(s) | 56 hour(s) | Open | 0% | bar: WEEK 5 M 13; WEEK 5 R 16 to WEEK 6 F 24; WEEK 7 R 30 to WEEK 8 T 4; WEEK 9 R 13
| Review Annotated Data | NSL team |  | Medium | 2020-07-17 | 2020-07-28 | 8 day(s) | 64 hour(s) | Open | 0% | bar: WEEK 5 M 13; WEEK 5 F 17 to WEEK 7 T 28; WEEK 7 R 30 to WEEK 8 T 4; WEEK 9 R 13
| Data Preprocessing |  |  | Medium | 2020-07-29 | 2020-07-29 | 1 day(s) | 8 hour(s) | Open | 1% | bar: WEEK 5 M 13; WEEK 7 W 29 to WEEK 8 T 4; WEEK 9 R 13
| Model Building : Iteration 1 Training | Saiful |  | Medium | 2020-07-30 | 2020-08-07 | 7 day(s) | 56 hour(s) | Open | 0% | bar: WEEK 5 M 13; WEEK 7 R 30 to WEEK 8 F 7; WEEK 9 R 13
| Model Building : Iteration 1 Testing | Saiful Kazal |  | Medium | 2020-08-10 | 2020-08-10 | 1 day(s) | 8 hour(s) | Open | 0% | bar: WEEK 5 M 13; WEEK 7 R 30 to WEEK 8 T 4; WEEK 9 M 10; WEEK 9 R 13
| Model Building : Iteration 2 Training | Saiful |  | Medium | 2020-08-12 | 2020-08-20 | 7 day(s) | 56 hour(s) | Open | 0% | bar: WEEK 5 M 13; WEEK 7 R 30 to WEEK 8 T 4; WEEK 9 W 12 to WEEK 10 R 20
| Model Building : Iteration 2 Testing | Saiful Kazal |  | Medium | 2020-08-21 | 2020-08-21 | 1 day(s) | 8 hour(s) | Open | 0% | bar: WEEK 5 M 13; WEEK 7 R 30 to WEEK 8 T 4; WEEK 9 W 12 to WEEK 9 R 13; WEEK 10 F 21
| Model Building : Iteration 3 Training | Saiful |  | Medium | 2020-08-12 | 2020-08-20 | 7 day(s) | 56 hour(s) | bar: WEEK 5 M 13; WEEK 7 R 30 to WEEK 8 T 4; WEEK 9 W 12 to WEEK 10 R 20
| Model Building : Iteration 3 Testing | Saiful |  | Medium | 2020-08-21 | 2020-08-21 | 1 day(s) | 8 hour(s) | bar: WEEK 5 M 13; WEEK 7 R 30 to WEEK 8 T 4; WEEK 9 R 13; WEEK 10 F 21
| Model Building : Iteration 4 Training including JP data | saiful |  | Medium | 2020-08-12 | 2020-08-20 | 7 day(s) | 56 hour(s) | Open | bar: WEEK 5 M 13 to WEEK 5 T 14; WEEK 7 R 30 to WEEK 8 T 4; WEEK 9 W 12 to WEEK 10 R 20
| Model Building : Iteration 4 Testing including JP data | saiful |  | Medium | 2020-08-21 | 2020-08-21 | 1 day(s) | 8 hour(s) | Open | bar: WEEK 5 M 13 to WEEK 5 T 14; WEEK 7 R 30 to WEEK 8 T 4; WEEK 9 R 13; WEEK 10 F 21
| Unit testing And performance measure | Kazal Saiful |  | Medium | 2020-08-10 | 2020-08-16 | 5 day(s) | 40 hour(s) | Open | 0% | bar: WEEK 5 M 13; WEEK 7 R 30 to WEEK 8 T 4; WEEK 9 R 13; WEEK 10 F 21 to WEEK 12 F 4
| Code Cleaning | Saiful |  | Medium | 2020-08-06 | 2020-08-06 | 1 day(s) | 8 hour(s) | Open | 0% | bar: WEEK 5 M 13; WEEK 7 R 30 to WEEK 8 T 4; WEEK 8 R 6; WEEK 9 R 13
| Documentation | Saiful |  | Medium | 2020-08-07 | 2020-08-07 | 1 day(s) | 8 hour(s) | Open | 0% | bar: WEEK 5 M 13; WEEK 7 R 30 to WEEK 8 T 4; WEEK 8 F 7; WEEK 9 R 13
Task | Subtask | Resource |  |  | 2020-07-21 | 2020-09-01 | 31 day(s) | 248 hour(s) | bar: WEEK 5 M 13; WEEK 7 R 30 to WEEK 8 T 4; WEEK 9 R 13
Table Text Detection | Table text Annotated data cropping from layout annotation | nahid |  | Medium | 2020-07-21 | 2020-07-22 | 2 day(s) | 16 hour(s) | Open | 0% | bar: WEEK 5 M 13; WEEK 6 T 21 to WEEK 6 W 22; WEEK 7 R 30 to WEEK 8 T 4; WEEK 9 R 13; WEEK 11 M 24 to WEEK 11 T 25
| Review Annotated Data | nahid |  | Medium | 2020-07-23 | 2020-07-27 | 3 day(s) | 24 hour(s) | Open | 0% | bar: WEEK 5 M 13; WEEK 6 R 23 to WEEK 7 M 27; WEEK 7 R 30 to WEEK 8 T 4; WEEK 9 R 13; WEEK 11 M 24 to WEEK 11 T 25
| Data preparation | nahid |  |  | 2020-07-28 | 2020-07-29 | 2 day(s) | 16 hour(s) | Open | bar: WEEK 5 M 13; WEEK 7 T 28 to WEEK 8 R 6; WEEK 9 R 13; WEEK 11 M 24 to WEEK 11 T 25
| Model Building : Iteration 1 Training | nahid |  | Medium | 2020-07-30 | 2020-08-10 | 8 day(s) | 64 hour(s) | Open | 0% | bar: WEEK 5 M 13; WEEK 7 R 30 to WEEK 9 M 10; WEEK 9 R 13; WEEK 11 M 24 to WEEK 11 T 25
| Model Building : Iteration 1 Testing | nahid |  | Medium | 2020-08-11 | 2020-08-11 | 1 day(s) | 8 hour(s) | Open | 0% | bar: WEEK 5 M 13; WEEK 7 R 30 to WEEK 8 R 6; WEEK 9 T 11; WEEK 9 R 13; WEEK 11 M 24 to WEEK 11 T 25
| Model Building : Iteration 2 Training | nahid |  | Medium | 2020-08-13 | 2020-08-24 | 8 day(s) | 64 hour(s) | Open | 0% | bar: WEEK 5 M 13; WEEK 7 R 30 to WEEK 8 T 4; WEEK 9 R 13 to WEEK 11 T 25
| Model Building : Iteration 2 Testing | nahid |  | Medium | 2020-08-25 | 2020-08-25 | 1 day(s) | 8 hour(s) | Open | 0% | bar: WEEK 5 M 13; WEEK 7 R 30 to WEEK 8 T 4; WEEK 9 R 13 to WEEK 10 W 19; WEEK 11 M 24 to WEEK 11 T 25
| Model Building : Iteration 3 Testing | nahid |  | Medium | 2020-08-13 | 2020-08-24 | 8 day(s) | 64 hour(s) | bar: WEEK 5 M 13; WEEK 7 R 30 to WEEK 9 T 11; WEEK 9 R 13 to WEEK 11 T 25
| Model Building : Iteration 3 Testing | nahid |  | Medium | 2020-08-25 | 2020-08-25 | 1 day(s) | 8 hour(s) | bar: WEEK 5 M 13; WEEK 7 R 30 to WEEK 8 R 6; WEEK 9 T 11; WEEK 9 R 13; WEEK 11 M 24 to WEEK 11 T 25
| Model Building : Iteration 4 Training including JP data | nahid |  | Medium | 2020-08-13 | 2020-08-24 | 8 day(s) | 64 hour(s) | Open | bar: WEEK 5 M 13 to WEEK 5 T 14; WEEK 7 R 30 to WEEK 8 T 4; WEEK 9 R 13 to WEEK 11 M 24
| Model Building : Iteration 4 Testing including JP data | nahid |  | Medium | 2020-08-25 | 2020-08-25 | 1 day(s) | 8 hour(s) | Open | bar: WEEK 5 M 13 to WEEK 5 T 14; WEEK 7 R 30 to WEEK 8 T 4; WEEK 9 R 13; WEEK 11 M 24 to WEEK 11 T 25
| Unit testing And performance measure | kazal |  | Medium | 2020-08-26 | 2020-09-01 | 5 day(s) | 40 hour(s) | bar: WEEK 5 M 13; WEEK 7 R 30 to WEEK 8 R 6; WEEK 9 R 13; WEEK 11 M 24 to WEEK 12 T 1
| Code Cleaning | nahid |  | Medium | 2020-08-14 | 2020-08-14 | 1 day(s) | 8 hour(s) | Open | 0% | bar: WEEK 5 M 13; WEEK 7 R 30 to WEEK 8 R 6; WEEK 9 M 10 to WEEK 9 F 14; WEEK 10 T 18 to WEEK 10 R 20; WEEK 11 M 24 to WEEK 11 T 25
| Documentation | nahid |  | Medium | 2020-08-17 | 2020-08-17 | 1 day(s) | 8 hour(s) | Open | 0% | bar: WEEK 5 M 13; WEEK 7 R 30 to WEEK 10 M 17; WEEK 10 W 19 to WEEK 11 T 25
Task | Subtask | Resource |  |  | 2020-07-30 | 2020-09-08 | 29 day(s) | 232 hour(s) | bar: WEEK 5 M 13; WEEK 7 R 30 to WEEK 9 R 13; WEEK 10 M 17 to WEEK 10 W 19
Text Recognition | Data semi automation | saiful |  | Medium | 2020-07-30 | 2020-07-31 | 2 day(s) | 16 hour(s) | Open | 0% | bar: WEEK 5 M 13; WEEK 7 R 30 to WEEK 8 T 4; WEEK 9 R 13
| Annotation of data | saiful |  | Medium | 2020-08-03 | 2020-08-13 | 9 day(s) | 72 hour(s) | Open | 0% | bar: WEEK 5 M 13; WEEK 7 R 30 to WEEK 9 R 13
| Review Annotated Data | saiful |  | Medium | 2020-08-04 | 2020-08-17 | 10 day(s) | 80 hour(s) | Open | 0% | bar: WEEK 5 M 13; WEEK 7 R 30 to WEEK 10 M 17; WEEK 10 W 19 to WEEK 10 F 21
| Data Preprocessing for Text recognition | saiful |  | Medium | 2020-08-18 | 2020-08-18 | 1 day(s) | 8 hour(s) | Open | 0% | bar: WEEK 5 M 13; WEEK 7 R 30 to WEEK 8 T 4; WEEK 9 R 13; WEEK 10 T 18 to WEEK 10 F 21
| Data Augmentation |  |  | Medium | 2020-08-04 | 2020-08-25 | 16 day(s) | 128 hour(s) |  | 0%
| planning and scripting | Mehadi,saiful |  | Medium | 2020-08-04 | 2020-08-12 | 7 day(s) | 56 hour(s) |  | 0%
| data generation | Mehadi,saiful |  | Medium | 2020-08-11 | 2020-08-17 | 5 day(s) | 40 hour(s) |  | 4%
| Review | Mehadi,saiful |  | Medium | 2020-08-18 | 2020-08-25 | 6 day(s) | 48 hour(s) |  | 5%
| Model Building : Iteration 1 Training | saiful |  | Medium | 2020-08-19 | 2020-08-27 | 7 day(s) | 56 hour(s) | Open | 0% | bar: WEEK 5 M 13; WEEK 7 R 30 to WEEK 8 T 4; WEEK 9 R 13; WEEK 10 W 19 to WEEK 11 R 27
| Model Building : Iteration 1 Testing | saiful |  | Medium | 2020-08-28 | 2020-08-28 | 1 day(s) | 8 hour(s) | Open | 0% | bar: WEEK 5 M 13; WEEK 7 R 30 to WEEK 8 T 4; WEEK 9 R 13; WEEK 10 W 19 to WEEK 10 F 21; WEEK 11 F 28
| Model Building : Iteration 2 Training | saiful |  | Medium | 2020-08-31 | 2020-09-07 | 6 day(s) | 48 hour(s) | Open | 0% | bar: WEEK 5 M 13; WEEK 7 R 30 to WEEK 8 T 4; WEEK 9 R 13; WEEK 10 W 19 to WEEK 10 F 21; WEEK 12 M 31 to WEEK 13 M 7
| Model Building : Iteration 2 Testing | saiful |  | Medium | 2020-09-08 | 2020-09-08 | 1 day(s) | 8 hour(s) | Open | 0% | bar: WEEK 5 M 13; WEEK 7 R 30 to WEEK 8 T 4; WEEK 9 R 13; WEEK 10 W 19 to WEEK 10 F 21; WEEK 13 T 8
| Model Building : Iteration 3 Training | saiful |  | Medium | 2020-08-31 | 2020-09-07 | 6 day(s) | 48 hour(s) | bar: WEEK 5 M 13; WEEK 7 R 30 to WEEK 8 T 4; WEEK 9 R 13; WEEK 10 W 19 to WEEK 10 F 21; WEEK 12 M 31 to WEEK 13 M 7
| Model Building : Iteration 3 Testing | saiful |  | Medium | 2020-09-08 | 2020-09-08 | 1 day(s) | 8 hour(s) | Open | 0% | bar: WEEK 5 M 13; WEEK 7 R 30 to WEEK 8 T 4; WEEK 9 R 13; WEEK 10 W 19 to WEEK 10 F 21; WEEK 13 T 8
| Model Building : Iteration 4 Training including JP data | saiful |  | Medium | 2020-08-31 | 2020-09-07 | 6 day(s) | 48 hour(s) | Open | bar: WEEK 5 M 13 to WEEK 5 T 14; WEEK 7 R 30 to WEEK 8 T 4; WEEK 9 R 13; WEEK 10 W 19 to WEEK 10 F 21; WEEK 12 M 31 to WEEK 13 W 9
| Model Building : Iteration 4 Testing including JP data | saiful |  | Medium | 2020-09-08 | 2020-09-08 | 1 day(s) | 8 hour(s) | Open | bar: WEEK 5 M 13 to WEEK 5 T 14; WEEK 7 R 30 to WEEK 8 T 4; WEEK 9 R 13; WEEK 10 W 19 to WEEK 10 F 21; WEEK 12 M 31 to WEEK 13 W 9
| Unit testing And performance measure | kazal data |  | Medium | 2020-09-01 | 2020-09-08 | 6 day(s) | 48 hour(s) | bar: WEEK 5 M 13; WEEK 7 R 30 to WEEK 8 T 4; WEEK 9 R 13; WEEK 10 W 19 to WEEK 10 F 21; WEEK 12 T 1 to WEEK 13 T 8
| Code Cleaning | saiful |  | Medium | 2020-09-02 | 2020-09-02 | 1 day(s) | 8 hour(s) | Open | 0% | bar: WEEK 5 M 13; WEEK 7 R 30 to WEEK 8 T 4; WEEK 9 R 13; WEEK 10 W 19 to WEEK 10 F 21; WEEK 12 W 2; WEEK 13 W 9
| Documentation | saiful |  | Medium | 2020-09-03 | 2020-09-03 | 1 day(s) | 8 hour(s) | Open | 0% | bar: WEEK 5 M 13; WEEK 7 R 30 to WEEK 8 T 4; WEEK 9 R 13; WEEK 10 W 19 to WEEK 10 F 21; WEEK 12 R 3
Task | Subtask | Resource |  |  | 2020-08-20 | 2020-09-21 | 23 day(s) | 184 hour(s) | bar: WEEK 5 M 13; WEEK 7 R 30 to WEEK 8 T 4; WEEK 9 R 13; WEEK 10 W 19 to WEEK 10 F 21
Core Modules Integration | Collect All Models and Modules | saiful and nahid |  | Medium | 2020-08-20 | 2020-08-20 | 1 day(s) | 8 hour(s) | Open | 0% | bar: WEEK 5 M 13; WEEK 7 R 30 to WEEK 8 T 4; WEEK 9 R 13; WEEK 10 W 19 to WEEK 10 F 21
| Integrate All Modules | saiful and nahid |  | Medium | 2020-08-20 | 2020-08-27 | 6 day(s) | 48 hour(s) | Open | 0% | bar: WEEK 5 M 13; WEEK 7 R 30 to WEEK 8 T 4; WEEK 9 R 13; WEEK 10 W 19 to WEEK 10 R 20; WEEK 11 M 24; WEEK 11 W 26 to WEEK 11 R 27
| Test Integrated Modules | saiful and nahid |  | Medium | 2020-09-10 | 2020-09-10 | 1 day(s) | 8 hour(s) | Open | 0% | bar: WEEK 5 M 13; WEEK 7 R 30 to WEEK 8 T 4; WEEK 9 R 13; WEEK 10 W 19 to WEEK 10 F 21; WEEK 13 R 10
| Unit testing And performance measure | kazal |  | Medium | 2020-09-11 | 2020-09-21 | 7 day(s) | 56 hour(s) | Open | 0% | bar: WEEK 5 M 13; WEEK 7 R 30 to WEEK 8 T 4; WEEK 9 R 13; WEEK 10 W 19 to WEEK 10 F 21; WEEK 13 F 11 to WEEK 15 M 21
| Code Cleaning | saiful and nahid |  | Medium | 2020-09-09 | 2020-09-09 | 1 day(s) | 8 hour(s) | Open | 0% | bar: WEEK 5 M 13; WEEK 7 R 30 to WEEK 8 T 4; WEEK 9 R 13; WEEK 10 W 19 to WEEK 10 F 21; WEEK 13 W 9
| Documentation | saiful and nahid |  | Medium | 2020-09-11 | 2020-09-11 | 1 day(s) | 8 hour(s) | Open | 0% | bar: WEEK 5 M 13; WEEK 7 R 30 to WEEK 8 T 4; WEEK 9 R 13; WEEK 10 W 19 to WEEK 10 F 21; WEEK 13 F 11
Task | Subtask | Resource |  |  | 2020-09-01 | 2020-09-22 | 16 day(s) | 128 hour(s) | bar: WEEK 5 M 13; WEEK 7 R 30 to WEEK 8 T 4; WEEK 9 R 13; WEEK 10 W 19 to WEEK 10 F 21
Web Integration | Collect Integrated Core Modules | saiful and apple |  | Medium | 2020-09-01 | 2020-09-01 | 1 day(s) | 8 hour(s) | Open | 0% | bar: WEEK 5 M 13; WEEK 7 R 30 to WEEK 8 T 4; WEEK 9 R 13; WEEK 10 W 19 to WEEK 10 F 21; WEEK 12 T 1
| Integrate With Web Application | saiful and apple |  | Medium | 2020-09-01 | 2020-09-04 | 4 day(s) | 32 hour(s) | Open | 0% | bar: WEEK 5 M 13; WEEK 7 R 30 to WEEK 8 T 4; WEEK 9 R 13; WEEK 10 W 19 to WEEK 10 F 21; WEEK 12 T 1 to WEEK 12 F 4
| Test Integrated Web Application | saiful and apple |  | Medium | 2020-09-07 | 2020-09-07 | 1 day(s) | 8 hour(s) | Open | 0% | bar: WEEK 5 M 13; WEEK 7 R 30 to WEEK 8 T 4; WEEK 9 R 13; WEEK 10 W 19 to WEEK 10 F 21; WEEK 13 M 7
| Unit testing And performance measure | kazal and saiful |  | Medium | 2020-09-15 | 2020-09-22 | 6 day(s) | 48 hour(s) | Open | 0% | bar: WEEK 5 M 13; WEEK 7 R 30 to WEEK 8 T 4; WEEK 9 R 13; WEEK 10 W 19 to WEEK 10 F 21; WEEK 14 T 15 to WEEK 15 T 22
| Code Cleaning | saiful and apple |  | Medium | 2020-09-16 | 2020-09-16 | 1 day(s) | 8 hour(s) | Open | 0% | bar: WEEK 5 M 13; WEEK 7 R 30 to WEEK 8 T 4; WEEK 9 R 13; WEEK 10 W 19 to WEEK 10 F 21; WEEK 14 W 16
| Documentation | saiful and apple |  | Medium | 2020-09-17 | 2020-09-17 | 1 day(s) | 8 hour(s) | Open | 0% | bar: WEEK 5 M 13; WEEK 7 R 30 to WEEK 8 T 4; WEEK 9 R 13; WEEK 10 W 19 to WEEK 10 F 21; WEEK 14 R 17
Formulas:
Start = IF(MIN([Start, row below]:H20)>0,MIN([Start, row below]:H20),"")
End Date = IF(MAX([End Date, row below]:I20)>0,MAX([End Date, row below]:I20))
Duration = IF(OR([Start]="",[End Date]=""),"",NETWORKDAYS([Start],[End Date])& " day(s)")
Duration = IF(OR([Start]=0,[End Date]=0),"",NETWORKDAYS([Start],[End Date])& " day(s)")
Duration in hours = IF(OR([Start]=0,[End Date]=0),"",NETWORKDAYS([Start],[End Date])*8& " hour(s)")